## Document Control
Document Control
Document History
Issue | Date | Maintainer/Owner | Description
1 | 2016-05-25 | Tufail Ahmed | Requirement Gathering Session Activity Planning - Day Wise
2
Supporting Document Attached
1 | Requirement Template
2

## Day Activity
Day wise Activity List for client interaction
Day | Date | Task | Action Items | Status | Remarks
1 | 2016-05-31 | Onboarding | 1) Report to ITC InfoTech US On-Boarding Team. | Not Started
|  |  | 2) Complete all joining formalities . | Not Started
|  |  | 3) Obtain PSID and Email ID .Share with Offshore Team. | Not Started
|  |  | 4) Travel to Client Office and Report there. | Not Started
|  |  | 5) Identify SPOC from client side who can facilitate logistics and other day to day requirement. | Not Started
|  |  | 6) Do high level stakeholder identification and prepare Stakeholder document to start next step. | Not Started
|  |  | 7) Study the nature of business of client and capture their expectation out of this Project. | Not Started
2 | 2016-06-01 | Requirement Study | 1) Setup meeting with offshore team to discuss communication Plan with Offshore team | Not Started
|  |  | 2) KickOff Meeting | Not Started
|  |  | 3) Study SOW and understand all In-Scope and Out of Scope. | Not Started
|  |  | 4) Use Template sheet as starting Point for Requirement Sheet. | Not Started
|  |  | 5) Discuss with Client next 8 days of activities and approach of requirement study. | Not Started
|  |  | 7) Start requirement study with Module 1 - Product , and Catalog management | Not Started
|  |  | 8) Capture all the Data and draft in Requirement Study template. | Not Started
3 | 2016-06-02 | Requirement Study | 1) Meeting with Offshore Team discuss status update and share the study docs | Not Started
|  |  | 2) Requirement Study of Module -1 Customer management. | Not Started
|  |  | 3) Review and validate scope and finalize module 1 doc. | Not Started
4 | 2016-06-03 | Requirement Study | 1) Meeting with Offshore Team discuss status update and share the study docs
2) Requirement Study of Module -2 Order management and Marketing Promotion.
3) Capture all the Data and draft in Requirement Study template.
5 | 2016-06-06 | Requirement Study | 1) Meeting with Offshore Team discuss status update and share the study docs
2) Requirement Study of Module -2 Analytics and Reports
3) Review and validate scope and finalize module 2 doc.
6 | 2016-06-07 | Requirement Study | 1) Meeting with Offshore Team discuss status update and share the study docs
2) Requirement Study of Module -3 Custom and 3rd party
3) Capture all the Data and draft in Requirement Study template.
7 | 2016-06-08 | Requirement Study | 1) Meeting with Offshore Team discuss status update and share the study docs
2) Requirement Study of Module -3 data migration.
3) Review and validate scope and finalize module 3 doc.
8 | 2016-06-09 | Requirement Study | 1) Meeting with Offshore Team discuss Prototype design
2) Conduct Walkthrough the Designs with client.
3) Collect Feedback and share with offshore team
9 | 2016-06-10 | Requirement Study | 1) Meeting with Offshore Team discuss Prototype design
2) Finalize the Design and take sign off
10 | 2016-06-13 | Requirement Study | 1) Meeting with Offshore Team discuss status update
2) Identify any CR in requirement and document it and freeze the Requirement.
2) Consolidate all requirement and do Internal review
3) Get sign off from client on Requirement.

## Instructions
| Steps | Details
1) | Identify Requirement from SOW | Name the requirement attach unique number link with module and sub module
2) | Define the Requirement | Clear write 1 line definition of requirement
3) | Elaborate the Requirement | Elaborate with Example Scenario Screenshot Business process Business rule
4) | Transfer to document | Use Template to Document of all captured data

## Day 1
Module | Functionality / Description
Product Browsing | § Multiple Images Per Product
§ Product Image Zoom-in Capability
§ Product Reviews
§ Related Products
§ Stock Availability
§ Multi-Tier Pricing
§ Up selling
§ Product Option Selection
§ Grouped Products View
§ Add to Wish list
§ Send product information to a Friend with Email
§ By Tutorials
§ Product Ratings
§ Loyalty points
§ Bundle products
Catalogue Management | § Platform supports multi-level catalogue listing.
§ Inventory Management with Backordered items, Minimum and Maximum quantities
§ Batch Updates to products in admin panel
§ Simple, Configurable (e.g. size, colour, etc.), Bundled and Grouped Products
§ Virtual Products
§ Downloadable/Digital Products
§ Tax Rates per location, customer group and product type
§ Advanced Pricing Rules and support for Special Prices
§ Search Results rewrites and redirects
§ Approve, Edit and Delete Product Tags
§ Approve, Edit and Delete Product Reviews

## DAY 2
Module | Functionality / Description
Customer Accounts | § Re-orders from account
§ Recently ordered items
§ Downloadable Products
§ Address Book with unlimited addresses
§ Default Billing and Shipping addresses
§ Wish list with ability to add comments
§ Newsletter Subscription management
§ Product Reviews submitted
§ Product Tags submitted
§ Account Dashboard for overview of: recent orders, personal information, newsletter subscription status, primary billing address, primary shipping address, shopping cart, wish list, recently ordered items, recently reviews and recent tags
§ View finalized orders and respective quantities
§ View confirmed orders from SUNDIAL
§ View wish list
§ Manage wish list
§ View of all items on Wish-list across users
§ Loyalty points management
§ Shipping status and tracking numbers
§ Customer groups
Customer Service | § Contact Us form
§ Order History with Status Updates
§ Order Tracking from Account
§ Forgot Password Email from front-end and administration panel
§ Order and Account Update Emails
§ Create and Edit Orders from the Admin Panel
§ Notification of gift messages if included along with special instructions
§ Email user when out of stock items on wish list is in stock.
Customer Accounts | § Re-orders from account
§ Recently ordered items
§ Downloadable Products
§ Address Book with unlimited addresses
§ Default Billing and Shipping addresses
§ Wish list with ability to add comments
§ Newsletter Subscription management
§ Product Reviews submitted
§ Product Tags submitted
§ Account Dashboard for overview of: recent orders, personal information, newsletter subscription status, primary billing address, primary shipping address, shopping cart, wish list, recently ordered items, recently reviews and recent tags
§ View finalized orders and respective quantities
§ View confirmed orders from SUNDIAL
§ View wish list
§ Manage wish list
§ View of all items on Wish-list across users
§ Loyalty points management
§ Shipping status and tracking numbers
§ Customer groups
Customer Service | § Contact Us form
§ Order History with Status Updates
§ Order Tracking from Account
§ Forgot Password Email from front-end and administration panel
§ Order and Account Update Emails
§ Create and Edit Orders from the Admin Panel
§ Notification of gift messages if included along with special instructions
§ Email user when out of stock items on wish list is in stock.
Analytics and Reports | § Admin Dashboard for Report Overview
§ Sales Reports
ü Sales by promotion
ü Sales by products
ü Sales by selection of products
ü Sales by time of day
ü Sales by customer
ü Real time sales report
ü Total Sales Invoiced
ü Total Sales Refunded
§ Least active customer account
§ No. of new customers daily/monthly/weekly
§ Tax Report
§ Abandoned Shopping Cart Report
§ Best Viewed Products Report
§ Best Purchased Products Report
§ Low Stock Report
§ Search Terms Report
§ Product Reviews Report
§ Tags Report
§ Coupon Usage Report
§ Best Customers Report by Total and Number of Orders
§ Integration with Google Analytics (GA)
Account Administration | § Admin Console to assign roles and user access rights
§ Ability to restrict catalogue access by customer hierarchy or product hierarchy based on geo, customer type etc.,
§ Mass upload & Download of product master, customer master, catalogue with product images & Price master
§ Ability to define workflow by customer hierarchy for approval of order confirmations within SUNDIAL Sales organisation
§ Ability to mass upload finalised order quantities against customer orders post offline rationalization process
Customized Modules | § Physical Gift Card – Website users can give gift coupon code to other users. Receiving users can utilize this coupon code for the new order.
§ Physical Coupons – The system will generate Coupon Code (not Bar Code) as configured by the Admin User.
§ Loyalty Program-
o Sundial can create a loyalty program based on the total order value spend by each customer.
o Extension does not use Magento sales rule to configure any free/add-on products as per points/loyalty tier.
o Allows to create unlimited number of loyalty programs with different rewards structure.
o Products can be included/excluded for a limited period of time.
o Include or exclude individual customers tier/group.
o Customers can view their statistics in their account center
o Ref: https://www.sweettoothrewards.com
§ Unified Tax Structure, reporting, and returns (Avatax) – Tax calculation typically processed during checkout but may also happen at estimation, shipping cart. When the order is placed, it is not immediately recorded in AvaTax. Tax amounts are calculated for the order when the customer places the order, but nothing is recorded in Avalara until a new invoice or credit memo is created. Batch process or Cron job will execute the sync between Magento and Avatax. Data mapping will be done between Magento and Avatax. Address validation recommended before placing order. Tax rules will have to be configured in Avatax rather than Magento Backend. Reference: https://www.avalara.com/tax-type/sales-and-use-tax/avatax/
§ Automatic language translation and on the fly switching for customer – By switching language from selector or by customer region the language will be switched to customer preference language. Ref: www.motionpoint.com
§ Automated social feeds - Allows you to display latest feeds from Livefyre. Ref: www.motionpoint.com
§ E-gift cards – Send Gift Card to friends or buy for themselves. Receive Gift Cards either online via email. Use Gift Cards either as discount coupons or store credit. Personalize Gift Cards with provided templates or upload their own image
§ PunchOut integration - PunchOut Catalogs, a supplier’s catalog content and products are readily and easily accessible within the buyer’s procurement system.
o Features –
ü Customize pricing and pricing tiers to each buying organization
ü Customize catalog for buyers group
ü Customize Store design for specific User
ü Ref: www.punchout2go.com
§ Automated Collection Launch - Ability to show the new/latest/featured collection of product which tagged in product management
§ ShipStation Integration – ShipStation is a web-based shipping solution that allows you to create shipping labels for all major carriers. ShipStation downloads Magento orders from Magento in real-time, allows you to create USPS, UPS, FedEx, DHL, and Canada Post shipping labels and packing slips in batch, and communicates tracking information to your customers. ShipStation extension need to install and configure with ShipStation properties to work with ShipStation services through Webservice call.
§ Megamenu - Megamenu is responsive Magento menu which will display category navigation in menu with lot of features and fully manage from admin side. You can display video and images of particular category in dropdown which is best for marketing. Admin can set subcategory and products in slider for particular category
§ CMS Tree Management and templates for generic CMS page types - The templates have to be defined. The user can edit the content based on template.
§ Manage free samples from multiple options - To give away free samples to the customers in the form of small sachet, trial packs of their products to choose from those freebies. For Example: 1. Get 2 exclusive samples free on the purchase of 500$ from the store. 2. Get 5 Shampoo sachet trial packs free on the purchase of soap. User can select and add allowed number of Free Samples to the cart based on the rules/range/limits set in the cart rules by admin.
§ Ability to offer discounts to recurring orders - Allow Sundial to sell products on a daily, weekly, monthly, or yearly recurring basis with any duration. Offer a magazine subscription for one year with a weekly periodicity or coffee delivery each three weeks. Prices of subscription intervals can also vary from each other and you can set them up in the way admin configure.
§ Ability to display video in carousel - Admin will upload video and configure options like display order, from & to date etc. Video will then be published on the front end
§ Integrate product information into CMS content. For example Shop this story – While creating CMS page, Products can be appended into the content. So that customer can add it to cart from CMS page.
§ Promotional "ads" show up on product pages and content pages - Allows to create blocks to add it in any position in page or options like only on selected pages, only to selected customer groups, on selected date only, on selected products only
§ Community commerce product Options - 10% of total will be allocated to community wallet if the customer buys a community commerce product. Admin can set the percentage of amount to allocate on each order, Review the total amount and customer/order history.
§ 1-click shopping - Provide option to process cart checkout with preferred payment channel for individual product.
§ Additional payment options including: debit cards. apple pay and more
o Transaction does not store CVV information.
o Preferred payment gateways will be configured in the website in order to provide multiple payment options for end users.
o Post selecting the payment gateway, control will be passed to provider and user has to complete traction on respective payment gateway.
o Control will be given back post transaction along with payment status and further process of order finalization will be hooked in.
§ Pre-payment - Ordering items which are not in stock. Example Pre-order
§ Abandoned Cart Functionality - The Abandoned Cart Saver emails any customers who have added an item to their cart but left before completing checkout an invitation to complete their order. The emails are customizable, and can be combined with coupon codes entice your customer to continue shopping. You can send up to three different emails to a single customer.
§ Add to Cart - Adding products to cart without navigating to shopping cart page

## Day 3
Module | Functionality / Description
Order Management | § Includes ability to create new customer, or select existing customer and view shopping cart, wish list, last ordered items, and compared products list, as well as select addresses, give discounts and assign custom prices
§ Email Notifications of Orders
Checkout | § One-Page Checkout
§ SSL security support for orders on both front-end and back-end
§ Shipping to multiple addresses in one order
§ Checkout without account only
§ Shopping Cart with tax and shipping estimates
§ Checkout with account to use address book
§ Option to create account at beginning of checkout
§ Accept gift messages per order and per item
§ Saved Shopping Carts with configurable expiration time
§ Gift wrapping – Individual gift wrapping for product
Marketing and Promotions | § Flexible Coupons (pricing rules) with ability to restrict to stores, customer groups, time period, products, and categories.
§ For example: Percent Discount ¦ Fixed Amount Discount ¦ Free Shipping ¦ Buy x, get y free. ¦ Buy x, get y with percent or fixed amount discount ¦ Buy x, get free shipping on order ¦ Buy x, get percent discount ¦ Buy x, get fixed amount discount.
§ Catalog Promotional Pricing by percentage or fixed amount with ability to restrict stores, categories, products
§ Free Shipping Option
§ Multi-Tier Pricing for quantity discounts
§ Bundled Products
§ Customer Group-specific pricing and group-specific tier pricing
§ Landing Page Tool for Campaigns
§ Search Engine Friendly URL's
§ URL Rewrites
§ Recently Viewed Products
§ Recently Compared Items
§ New Items Promotional Tool
§ Up-sells in Shopping Cart
§ Cross-sells on product pages
§ Send to a Friend for all visitors, or registered users only
§ Send Wish list to a Friend by Email
§ Polls
§ Newsletter Management
§ Exclude items from promotion
§ View all active promotions
§ Allow or restrict overlapping promotions
§ Restrict promotion to specific time period
§ Restrict promotion to any master data property
§ Restrict promotion to recurring orders
§ Cross-sells on category pages
§ Ability for customer to bundle a selection of products
§ Integrate email with CMS
§ Manage Referrals- by referral code

## Day 4
Module | Functionality / Description
Analytics and Reports | § Admin Dashboard for Report Overview
§ Sales Reports
Sales by promotion
Sales by products
Sales by selection of products
Sales by time of day
Sales by customer
Real time sales report
Total Sales Invoiced
Total Sales Refunded
§ Least active customer account
§ No. of new customers daily/monthly/weekly
§ Tax Report
§ Abandoned Shopping Cart Report
§ Best Viewed Products Report
§ Best Purchased Products Report
§ Low Stock Report
§ Search Terms Report
§ Product Reviews Report
§ Tags Report
§ Coupon Usage Report
§ Best Customers Report by Total and Number of Orders
§ Integration with Google Analytics (GA)

## Day 5
Module | Functionality / Description
Customized Modules | § Physical Gift Card – Website users can give gift coupon code to other users. Receiving users can utilize this coupon code for the new order.
§ Physical Coupons – The system will generate Coupon Code (not Bar Code) as configured by the Admin User.
§ Loyalty Program-
o Sundial can create a loyalty program based on the total order value spend by each customer.
o Extension does not use Magento sales rule to configure any free/add-on products as per points/loyalty tier.
o Allows to create unlimited number of loyalty programs with different rewards structure.
o Products can be included/excluded for a limited period of time.
o Include or exclude individual customers tier/group.
o Customers can view their statistics in their account center
o Ref: https://www.sweettoothrewards.com
Unified Tax Structure, reporting, and returns (Avatax) – Tax calculation typically processed during checkout but may also happen at estimation, shipping cart. When the order is placed, it is not immediately recorded in AvaTax. Tax amounts are calculated for the order when the customer places the order, but nothing is recorded in Avalara until a new invoice or credit memo is created. Batch process or Cron job will execute the sync between Magento and Avatax. Data mapping will be done between Magento and Avatax. Address validation recommended before placing order. Tax rules will have to be configured in Avatax rather than Magento Backend. Reference: https://www.avalara.com/tax-type/sales-and-use-tax/avatax/
Automatic language translation and on the fly switching for customer – By switching language from selector or by customer region the language will be switched to customer preference language. Ref: www.motionpoint.com
Automated social feeds - Allows you to display latest feeds from Livefyre. Ref: www.motionpoint.com
§ E-gift cards – Send Gift Card to friends or buy for themselves. Receive Gift Cards either online via email. Use Gift Cards either as discount coupons or store credit. Personalize Gift Cards with provided templates or upload their own image
§ PunchOut integration - PunchOut Catalogs, a supplier’s catalog content and products are readily and easily accessible within the buyer’s procurement system.
o Features –
ü Customize pricing and pricing tiers to each buying organization
ü Customize catalog for buyers group
ü Customize Store design for specific User
ü Ref: www.punchout2go.com
§ Automated Collection Launch - Ability to show the new/latest/featured collection of product which tagged in product management
§ ShipStation Integration – ShipStation is a web-based shipping solution that allows you to create shipping labels for all major carriers. ShipStation downloads Magento orders from Magento in real-time, allows you to create USPS, UPS, FedEx, DHL, and Canada Post shipping labels and packing slips in batch, and communicates tracking information to your customers. ShipStation extension need to install and configure with ShipStation properties to work with ShipStation services through Webservice call.
§ Megamenu - Megamenu is responsive Magento menu which will display category navigation in menu with lot of features and fully manage from admin side. You can display video and images of particular category in dropdown which is best for marketing. Admin can set subcategory and products in slider for particular category
§ CMS Tree Management and templates for generic CMS page types - The templates have to be defined. The user can edit the content based on template.
§ Manage free samples from multiple options - To give away free samples to the customers in the form of small sachet, trial packs of their products to choose from those freebies. For Example: 1. Get 2 exclusive samples free on the purchase of 500$ from the store. 2. Get 5 Shampoo sachet trial packs free on the purchase of soap. User can select and add allowed number of Free Samples to the cart based on the rules/range/limits set in the cart rules by admin.
§ Ability to offer discounts to recurring orders - Allow Sundial to sell products on a daily, weekly, monthly, or yearly recurring basis with any duration. Offer a magazine subscription for one year with a weekly periodicity or coffee delivery each three weeks. Prices of subscription intervals can also vary from each other and you can set them up in the way admin configure.
§ Ability to display video in carousel - Admin will upload video and configure options like display order, from & to date etc. Video will then be published on the front end
§ Integrate product information into CMS content. For example Shop this story – While creating CMS page, Products can be appended into the content. So that customer can add it to cart from CMS page.
§ Promotional "ads" show up on product pages and content pages - Allows to create blocks to add it in any position in page or options like only on selected pages, only to selected customer groups, on selected date only, on selected products only
§ Community commerce product Options - 10% of total will be allocated to community wallet if the customer buys a community commerce product. Admin can set the percentage of amount to allocate on each order, Review the total amount and customer/order history.
§ 1-click shopping - Provide option to process cart checkout with preferred payment channel for individual product.
§ Additional payment options including: debit cards. apple pay and more
o Transaction does not store CVV information.
o Preferred payment gateways will be configured in the website in order to provide multiple payment options for end users.
o Post selecting the payment gateway, control will be passed to provider and user has to complete traction on respective payment gateway.
o Control will be given back post transaction along with payment status and further process of order finalization will be hooked in.
§ Pre-payment - Ordering items which are not in stock. Example Pre-order
§ Abandoned Cart Functionality - The Abandoned Cart Saver emails any customers who have added an item to their cart but left before completing checkout an invitation to complete their order. The emails are customizable, and can be combined with coupon codes entice your customer to continue shopping. You can send up to three different emails to a single customer.
§ Add to Cart - Adding products to cart without navigating to shopping cart page

## Day 6
Module | Functionality / Description
Master Data | § Item Category
§ Items/SKU/ Materials
§ Upload Item picture
§ Unit of Measure (UoM)
§ States
§ Cities
§ Stores/ Locations
§ Configurable SKU
§ Title
§ Description
§ GTIN
§ Weight
§ Dimensions
§ Ingredients
§ Need state
§ Hair type
§ Hair concerns
§ Qualities
§ Color code
§ Usage information.

## Day 7
Protoype Design 1
Homepage | Catalog Page | Search Result Page
Main Menu | Mini Shopping Cart | Search Criteria
Search | Breadcrumb Trail | Sort By
Your Account | Change the List Style | Search Results
Feature a Brand | Sort the List | Show per Page
Offer a Promotion | Filter the List | Next Page
Offer a Discount | Go to Next Page | Advanced Search
Hear from an Expert | Read a Review
Appeal to a Lifestyle | Show More per Page
Shop by Category
Popular Products
Footer Links Block
Footer Content
Subscribe!

## Day 8
Protoype Design 2
Product Page | Shopping Cart Page | My Account Page | Static Pages
Mini Shopping Cart | One/Many Item in Cart | New Customers Register | About Us
Help | Change the Quantity | Customers Home Page | Contact Us
Product Rating | Estimate Shipping & Tax | Order History | Copyright Notice
Stock Availability | Go to Checkout | Order Tracking | Privacy Policy
Choose the Options | Edit Line Item | RE-Order | Cookie Law Compliance
Zoom | Update the Cart | Address Book
Buy it Now! | Checkout with Multiple Addresses | Wish List
Email a Friend | Use a Coupon
Add to Your Wish List | Cross-sells
Compare Products | Special Price
Thumbnail
Product Details
Add All to Cart
Related Products

## Day 9
Sl.No | Review / Comments | Date | Owner | Status | Freeze (Y/N)
Note: | This is to capture the changes in requirement and their status